## Fall 2026
[9 empty] | FIRST DAY | [13 empty] | Labor Day | [37 empty] | Fall Break | [37 empty] | Thanksgiving Break | [17 empty] | STUDY DAYS |  |  |  | FINALS WEEK
| Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat.
| 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19
PRODUCTIONS:
Mainstage Musical | [39 empty] | Rehearsal |  |  | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsal |  |  |  |  | Crew View |  |  |  | Spacing | Band Read | Spacing | Tech 1 | Tech 2 | Sitz | Dress 1 | Dress 2 | Dress 3 | Perf 1 | Perf 2 | Perf 3/4 | Perf 5
Build/Strike | [43 empty] | Construction | [5 empty] | Construction | [6 empty] | Construction | [6 empty] | Construction | [6 empty] | Pack Truck | [5 empty] | Load In | Load In |  | Tech Work Time | [5 empty] | Tech Work Time | [6 empty] | STRIKE
Mainstage Play | [9 empty] | Rehearsal |  |  |  |  | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsal |  |  |  |  | Crew View |  |  | Tech 1 | Tech 2 |  | Tech 3 | Dress 1 |  | Dress 2 | Dress 3 | Perf 1 | Perf 2 | Perf 3 | Perf 4 | Perf 5/6 | Perf 7
Build/Strike | [8 empty] | Construction/Installation | [5 empty] | Construction/Installation | [6 empty] | Construction/Installation | [6 empty] | Construction/Installation | [28 empty] | STRIKE
Kaleidoscope/Studio Show | [25 empty] | Kaleidoscope | [44 empty] | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsal |  |  |  |  | Crew View | [8 empty] | Tech 1 | Tech 2 | Dress 1 | Dress 2 | Perf 1 | Perf 2 | Perf 3/4 | Perf 5
Build/Strike | [113 empty] | STRIKE
Student Events | [91 empty] | APO Underclassmen Cabaret |  |  |  | Perf | [16 empty] | Directing/MT/Devised |  |  |  | TTBE- Blackout |  | Perf
Misc. Events | 2026-08-22: Auditions | Callbacks
Shorter tech for TTBE; Matinee Studio Perf; Evening Directing Tech
Chapel Hill
IMT
PepsiCo
Hays

## Spring 2027
[9 empty] | MLK Day | First Day | [53 empty] | Spring Break | [11 empty] | Good Friday | [40 empty] | STUDY DAYS |  |  |  | FINALS WEEK
| Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat. | Sun. | Mon. | Tues. | Wed. | Thur. | Fri. | Sat.
| 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15
PRODUCTIONS:
Mainstage Musical | [49 empty] | Rehersals | [6 empty] | Rehearsals | [14 empty] | Rehearsals | [5 empty] | Rehearsals | [6 empty] | Rehearsals |  |  |  |  | Crew View |  |  | Tech 1 | Tech 2 |  | Tech 3 | Dress 1 | Dress 2 | Dress 3 |  | Perf 1 | Perf 2 | Perf 3 | Perf 4 | Perf 5/6
Build/Strike | [85 empty] | Load In | [6 empty] | Load In | [12 empty] | STRIKE
Mainstage Play | [9 empty] | Rehearsals |  |  |  |  | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsal | [6 empty] | Rehearsals |  |  |  |  | Crew View |  |  | Tech 1 | Tech 2 |  | Tech 3 | Dress 1 |  | Dress 2 | Dress 3 | Perf 1 | Perf 2 | Perf 3 | Perf 4 | Perf 5/6 | Perf 7
Build/Strike
Kalidoscope: Choreo Stage | [31 empty] | Choreographer's Stage |  |  | Perf | Perf
Student Events | [83 empty] | TTBE | APO
Misc. Events | 2026-01-16: Auditions | Callbacks | [50 empty] | Showcase
Chapel Hill
PepsiCo
Hays
IMT
Stage West